## Summary
Kingsgate Place Office Development - cost summary FY26
Exported from FinOps on 18/09/2026 by R. Okafor - all amounts in GBP unless stated
COST CODE | Category | Vendor | approved_budget_(gbp) | Actual To Date | Variance | %_spent | notes
SUB-01 | Substructure and basement | Groundline Piling Ltd | 6200000 | 6620000 | -420000 | 1.0677 | per last month
FRM-01 | Structural steel frame | Brennan Steel Fabrications | 9400000 | 7850000 | 1550000 | 0.8351 | Fixed-price order placed October 2025; includes metal decking and stairs.
ENV-01 | Facade and curtain walling | Vitrana Facades Ltd | 7800000 | 2880000 | 4920000 | 0.3692 | Unitised curtain wall. Paid through a project bank account from July 2026.
MEP-01 | Mechanical, electrical and plumbing | Halden Building Services | 11500000 | 3650000 | 7850000 | 0.3174 | Includes lifts, BMS and the substation fit-out.
FIT-01 | Internal finishes and Cat A fit-out | Orwell Interiors | 5,200,000 | 180000 | 5020000 | 0.0346 | Raised floors, ceilings and core finishes. Tenant changes on levels 7-10 not yet priced.
PRE-01 | Preliminaries and site establishment | Fenwright Construction | 4900000 | 2.460.000,00 | 2440000 | 0.502 | Site management, welfare, hoarding, tower crane TC1 and scaffold.
DES-01 | Professional fees and design team |  | 2300000 | 1170000 | 1130000 | 0.5087 | Architect-led design team novated to the contractor at contract signature.
CON-01 | Contingency |  | 1900000 | 310000 | 1590000 | 0.1632 | n/a
| TOTAL |  | 49200000 | 25120000 | 24080000

## By Period
Category | 2025-Q4 | Q1 2026 | 2Q26 | Qtr 3 2026 | Total
Substructure and basement | 1850000 | 2300000 | 1650000 | 820000 | 6620000
Structural steel frame | 650000 | 1200000 | 2900000 | 3100000 | 7850000
Facade and curtain walling | 0 | 450000 | 780000 | 1650000 | 2880000
Mechanical, electrical and plumbing | 120000 | 380000 | 1100000 | 2050000 | 3650000
Internal finishes and Cat A fit-out | 0 | 0 | 0 | 180000 | 180000
Preliminaries and site establishment | 520000 | 610000 | 640000 | 690000 | 2460000
Professional fees and design team | 380000 | 290000 | 260000 | 240000 | 1170000
Contingency | 0 | 0 | 310000 | 0 | 310000

## Notes
Date | Author | Note
2026-02-18 | R. Okafor | Obstruction breakout in the north-east corner is being recorded on dayworks sheets against SUB-01. Not yet valued.
12/06/2026 | S. Carter | Contingency release for weekend steel erection shifts and the extended mobile crane hire approved by the client at the 12 June progress meeting.
03-Jul-26 | Commercial team | Project bank account opened for Vitrana Facades. From July, curtain wall payments go through the PBA and not direct to the subcontractor.
21 August 2026 | R. Okafor | Substructure final account agreed with Groundline. SUB-01 closes above its line budget.