## Summary
Conduit Unified LLM Gateway - cost summary FY26
Exported from FinOps on 18/09/2026 by H. Okonkwo - all amounts in USD unless stated
cost_code | category | VENDOR | Approved Budget (USD) | Actual To Date | Variance | % Spent | NOTES
ENG-01 | Platform engineering | In-house | 2400000 | 1.850.000,00 | 550000 | 0.7708 | Two squads: routing and billing.
ENG-02 | Reliability engineering |  | 780000 | 565000 | 215000 | 0.7244 | Grew after the May rate-limit incident.
MOD-01 | Provider token spend | Northstar / Corvus / Helion | 1450000 | 1585000 | -135000 | 1.0931 | tbc
INF-01 | Cloud and edge infrastructure | Stratus Cloud | 420000 | 280000 | 140000 | 0.6667 | see attached
OBS-01 | Observability and analytics | Lumen Observability | 165000 | 118000 | 47000 | 0.7152
SEC-01 | Security and SOC 2 audit | Ardent Security | 190000 | 130000 | 60000 | 0.6842 | Type I delivered in June; Type II window runs to November.
VEN-01 | Contract engineering | Northcape Labs | 610000 | 535000 | 75000 | 0.877 | Ramping down through October.
CON-01 | Contingency |  | 300,000 | 120000 | 180000 | 0.4 | Drawn down for the multi-region control plane.
| TOTAL |  | 6315000 | 5183000 | 1132000

## By Period
Category | 2025-Q4 | Q1 2026 | 2Q26 | Qtr 3 2026 | Total
Platform engineering | 310000 | 480000 | 520000 | 540000 | 1850000
Reliability engineering | 60000 | 140000 | 175000 | 190000 | 565000
Provider token spend | 95000 | 280000 | 520000 | 690000 | 1585000
Cloud and edge infrastructure | 38000 | 62000 | 84000 | 96000 | 280000
Observability and analytics | 18000 | 30000 | 34000 | 36000 | 118000
Security and SOC 2 audit | 0 | 45000 | 60000 | 25000 | 130000
Contract engineering | 120000 | 210000 | 165000 | 40000 | 535000
Contingency | 0 | 0 | 0 | 120000 | 120000

## Notes
Date | Author | Note
2026-02-05 | H. Okonkwo | Provider credits are pre-purchased each quarter and expire unused, so MOD-01 runs ahead of actual consumption early in a quarter.
02/07/2026 | Finance Ops | The evaluation harness run by the search team in May was charged to MOD-01; an internal chargeback to that team is still pending.
14-Aug-26 | A. Mehta | Contingency drawdown of 120k approved by the steering committee for the multi-region control plane.